## Sheet1
|  | ACTION PLAN |  |  |  |  | ACTION PLAN
|  | Promoting |  |  |  |  | People
Steps | Responsibility | Time (weeks) | Predecessor tasks | Resources | Steps | Responsibility | Time (weeks) | Predecessor tasks | Resources
1. Online |  |  |  |  | 1. Hire if not already in the company
a) Create online ads | Visual artist | 4 |  | Financial, Technical | a) Financial manager | CEO | 6 |  | Human
b) Show ads on own website | Developer | 6 | 1.a | Technical | b) Software developers | CEO | 6 |  | Human
c) Buy advertising time on social media | Marketing person | 5 | 1.a | Financial | c) Marketing personnel | CEO | 6 |  | Human
d) Contact partners and | Marketing person | 5 | 3 | Financial, Human | d) Maybe outsource visual arts (ads) | Financial manager | 6 |  | Financial, Human
acquire ad time on their websites
2. Big clothing brands
2. Direct marketing |  |  |  |  | a) Make contract with such companies | Marketing person | 15 | AP Promoting 3.a,b | Human
a) Email to free user accounts | Developer | 2 |  | Technical
3. Clients
3. Sponsorship marketing |  |  |  |  | a) Attract customers with free trial | Marketing person | 5 |  | Human, Technical
a) Contact possible partners | Marketing person | 8 |  | Human | b) Market directly to that type of users | Marketing person | 5 |  | Human, Technical
b) Organise showcase for product |  | 8 | 3.a | Financial | c) Urge to buy full version | Marketing person | 5 |  | Human, Technical
b1) Arrange necessary facility for event | Financial manager | 2 |  | Financial
b2) Plan showcase | Marketing person | 7 |  | Human
b3) Test product beforehand | Developer | 8 |  | Technical
b4) Invite possible partner | Marketing person | 8 |  | Human
c) Bargain partner to market product | Marketing person | 6 | 3.b | Human
alongside their own